Guide 2. APT Project Development

Capstone Course

- APT Project Progress Summary

Below, you will find various fields that you must fill out with the requested information.

| APT Project Progress Summary | The layout/diagramming for the improvements to the cabin rental system was carried out, including enhancements to the database normalization and the corresponding 4+1 diagrams for the features to be implemented in the system. |
| --- | --- |
| Objectives | The goal of the development is to create an intuitive web platform that allows users to easily explore and book cabins. The reservation process will be facilitated through an easy-to-use internal chat, improving communication and reducing response times. Additionally, maintainers/management modules will be implemented to manage cabins, reservations, and users efficiently, ensuring security and scalability for business growth. |
| Methodology | A classical software development methodology will be applied, with iterative stages including: - Analysis of functional and non-functional requirements. - Database design, use case diagrams, and activity diagrams. - Modular implementation by phases: authentication, reservations, payments, inventory. - Functionality testing, form validation, and data flow verification. - Technical and end-user documentation. |
| Progress Evidence | Links and screenshots of both the architecture and the GitHub repository where progress will be shown as commits. |
| 2. Work Plan Monitoring |  |
| Examine your work plan carefully, focusing especially on the progress status and adjustments columns. |  |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competence or Units | Activities | Resources | Duration | Responsible | Observations | Progress Status | Adjustments |
| APT Project | APT Project definition development: Propose a solution to the stated problem | Computer and document | 1 day | Entire team | Facilitator: Having the project defined since the final portfolio process sped up the start. | Completed | None. The original portfolio idea was maintained. |
| Project Management | Charter: Define the project charter | Computer and documents | 2 days | Jose Cisterna | Facilitator: Prior clarity of the scope and overall purpose facilitated the drafting. | Completed | Roles and responsibilities of the team were formalized. |
| Project Management | Requirement template: Define functional and non-functional requirements | Computer and documents | 2 days | Antonia Muñoz | Difficulty: Risk of hindering the plan if requirements were not well bounded. | Completed | Prioritization of key requirements for customer needs. |
| Project Management | SRS Report: Define the software requirements specification report | Computer and documents | 5 days | Daniel Parada | Facilitator: The previous conceptual baseline sped up drafting the SRS. | Completed | Adaptation of formats according to institutional guidelines. |
| Prototyping | Mockups: Create the graphical mockup of the system | Computer and PowerPoint | 4 days | Antonia Muñoz | Facilitator: Having a clear aesthetic and functional vision facilitated the design. | Completed | Adjustment of main screen flows based on requirements. |
| Project Management | Gantt Chart: Create the detailed activity schedule | Computer and documents | 4 days | Jose Cisterna | Facilitator: Prior milestone definitions guided scheduling. | Completed | Synchronization of timelines according to delivery deadlines. |
| Project Management | Extended use cases: Define use cases in detail | Computer and documents | 3 days | Bastian Garrido | Facilitator: Clear understanding of user roles and system interactions. | Completed | Refinement of alternative flows and exceptions. |
| Architecture | SAD Document: Define the software architecture document of the project | Computer and documents | 3 days | Entire team | Difficulty: Extensive document; required high internal coordination to avoid delays. | Completed | Division of technical sections among team members to optimize time. |
| Project Management | Data dictionary: Define system terminology and fields | Computer and documents | 1 day | Entire team | Facilitator: Prior familiarity with the business domain and technical concepts. | Completed | Standardization of attribute names with the database model. |
| APT Project | APT Project development: Second phase of technical implementation and development | Computer and documents | 43 days | Entire team | Difficulty: Technical workload volume may cause delays in time milestones. | In progress | Flexible re-allocation of workloads based on module complexity. |
| Databases | DB Model development and scripts: Creation of model, tables, and PL/SQL scripts | Computer, MySQL engine | 7 days | Entire team | Facilitator: Clear previous relational design; speeds up script writing. | In progress | Normalization of previous database for better scalability. |
| Programming | 100% system development: Programming of all software modules | Computer, Visual Studio Code | 25 days | Entire team | Difficulty: Learning curve when implementing functions/components not practiced before. | In progress | Restructuring, modular optimization, and code integration. |
| Quality | Test Plan: Define cases and criteria to validate software quality | Computer and documents | 15 days | Entire team | Difficulty: Executing tests poorly or late may cause unexpected failures in critical features. | Not started | Early scheduling of unit tests to avoid overloading the end phase. |
| Quality | Change control matrix: Manage modifications during the lifecycle | Computer and documents | 3 days | Entire team | Difficulty: Lack of clarity in changes creates disorder and rework. | Not started | Establishment of a single template to log requests and scopes. |
| Quality | Scope verification: Validate fulfillment of all agreed requirements | Computer and documents | 1 day | Entire team | Facilitator: Accelerated if development strictly adheres to SRS and standards. | Not started | Cross-comparison of delivered features against initial SRS. |
| Project Management | User manuals: Prepare step-by-step explanatory guide for the end user | Computer and documents | 1 day | Entire team | Difficulty/Facilitator: Lack of experience in technical writing vs. full mastery of the system. | Not started | Incorporation of sequential screenshots to facilitate reading. |
| Project Management | Project closure report: Formalize the end of the project | Computer and documents | 3 days | Entire team | Facilitator: Responsibility maintained throughout previous phases simplifies closure. | Not started | None; awaiting conclusion of technical phases. |
| APT Project | APT Final report: Third phase of development and consolidated final documentation | Computer and documents | 16 days | Entire team | Facilitator: Discipline and documentation generated in previous stages speed up delivery. | Not started | Progressive consolidation of annexes and partial reports. |
| APT Project | APT Presentation document: Preparation of presentation material and final presentation | Computer and documents | 2 days | Entire team | Facilitator: Mastery of the solution built throughout the process. | Not started | Visual synthesis focused on the problem statement, technical solution, and live demo. |

3. Adjustments Based on Monitoring

Elaborate on the observations in your work plan. Analyze the planned activities and indicate which aspects facilitated or hindered execution. Explain how you addressed and/or will address obstacles. Finally, point out any adjustments made to the work plan as a result of this analysis.

Factors that facilitated and/or hindered the development of my work plan: The main facilitator is the teamwork currently taking place for the project. Regarding future obstacles, if we support each other and document deliveries and technical development thoroughly, everything will proceed as planned.

Adjusted or eliminated activities: So far, it has not been necessary to make specific adjustments; rather, corrections and refinements were made to what was already planned from the beginning.

Activities not started or delayed: So far, deadlines have been met successfully thanks to the team; nothing is past due, and unstarted activities are simply waiting for their scheduled start date.